## Document Processing
MEDIAN v0.5.0 Document Processing Tracker | MEDIAN v0.5.0 Document Processing Tracker | MEDIAN v0.5.0 Document Processing Tracker | MEDIAN v0.5.0 Document Processing Tracker | MEDIAN v0.5.0 Document Processing Tracker | MEDIAN v0.5.0 Document Processing Tracker | MEDIAN v0.5.0 Document Processing Tracker | MEDIAN v0.5.0 Document Processing Tracker | MEDIAN v0.5.0 Document Processing Tracker | MEDIAN v0.5.0 Document Processing Tracker | MEDIAN v0.5.0 Document Processing Tracker | MEDIAN v0.5.0 Document Processing Tracker | MEDIAN v0.5.0 Document Processing Tracker
One row per current Gate 2 source, ordered by the intended processing sequence. Chunk counts are evidence-backed; legacy dry-run counts are explicitly distinguished from completed extraction. | One row per current Gate 2 source, ordered by the intended processing sequence. Chunk counts are evidence-backed; legacy dry-run counts are explicitly distinguished from completed extraction. | One row per current Gate 2 source, ordered by the intended processing sequence. Chunk counts are evidence-backed; legacy dry-run counts are explicitly distinguished from completed extraction. | One row per current Gate 2 source, ordered by the intended processing sequence. Chunk counts are evidence-backed; legacy dry-run counts are explicitly distinguished from completed extraction. | One row per current Gate 2 source, ordered by the intended processing sequence. Chunk counts are evidence-backed; legacy dry-run counts are explicitly distinguished from completed extraction. | One row per current Gate 2 source, ordered by the intended processing sequence. Chunk counts are evidence-backed; legacy dry-run counts are explicitly distinguished from completed extraction. | One row per current Gate 2 source, ordered by the intended processing sequence. Chunk counts are evidence-backed; legacy dry-run counts are explicitly distinguished from completed extraction. | One row per current Gate 2 source, ordered by the intended processing sequence. Chunk counts are evidence-backed; legacy dry-run counts are explicitly distinguished from completed extraction. | One row per current Gate 2 source, ordered by the intended processing sequence. Chunk counts are evidence-backed; legacy dry-run counts are explicitly distinguished from completed extraction. | One row per current Gate 2 source, ordered by the intended processing sequence. Chunk counts are evidence-backed; legacy dry-run counts are explicitly distinguished from completed extraction. | One row per current Gate 2 source, ordered by the intended processing sequence. Chunk counts are evidence-backed; legacy dry-run counts are explicitly distinguished from completed extraction. | One row per current Gate 2 source, ordered by the intended processing sequence. Chunk counts are evidence-backed; legacy dry-run counts are explicitly distinguished from completed extraction. | One row per current Gate 2 source, ordered by the intended processing sequence. Chunk counts are evidence-backed; legacy dry-run counts are explicitly distinguished from completed extraction.
Sources | 24 | Accepted legacy evidence | 4 | Fresh extraction not started | 12 | Reference / deterministic only | 6
Order | Processing phase | Source ID | Current filename | Content-derived role | Processing disposition | Chunks | Chunk-count basis | Extraction status | Accepted legacy records | Next action | Repository path | Notes
1 | Stage 2 — authorial stream | M050-SRC-AUTHORIAL-GRAMMAR-001 | M050_Authorial_Grammar_Orthography_and_Prose_Style_Guide_v0_1_MEDIANv0_5_0.md | Authorial grammar, orthography, and prose rules | Source-bounded atomic extraction | 50 | Legacy dry run only; recalculate under Gate 5 | Calibration rejected; fresh extraction required | 0 | Rebuild chunk plan offline, then approve one controlled calibration | m050/docs/v0.5/governance/M050_Authorial_Grammar_Orthography_and_Prose_Style_Guide_v0_1_MEDIANv0_5_0.md | The rejected call is preserved as failure evidence; it is not reusable output.
2 | Stage 2 — constitutional evidence | M050-SRC-PA-001 | M050_Governing_Philosophy_and_Architecture_v1_3_MEDIANv0_5_0.md | Constitutional game identity and architecture | Migrate grounded evidence into Layer E | 42 | Completed legacy run | Legacy accepted; migration repairs required | 346 | Re-derive controlled fields and preserve silent-state boundary | m050/docs/v0.5/governance/M050_Governing_Philosophy_and_Architecture_v1_3_MEDIANv0_5_0.md | No paid re-extraction required.
3 | Stage 2 — human rulings | M050-SRC-HUMAN-RULINGS-001 | M050_Human_Rulings_Ledger_v0_4_MEDIANv0_5_0.md | Mixed human rulings, lineage, and process evidence | Ruling-ID extraction plus deterministic partition | 47 | Completed legacy run | Legacy accepted evidence; deterministic reconstruction required | 173 | Reconstruct each HR section and rebuild stream partitions | m050/docs/v0.5/governance/M050_Human_Rulings_Ledger_v0_4_MEDIANv0_5_0.md | Legacy candidate is archived and cannot feed reconciliation unchanged.
4 | Stage 2 — ontology stream | M050-SRC-MSID-GRAMMAR-001 | M050_MSID_Grammar_v0_5_MEDIANv0_5_0.md | Ontology and identifier grammar | Migrate accepted ontology evidence | 30 | Completed legacy run | Legacy accepted; migration repairs required | 273 | Migrate evidence, then construct controlled vocabulary in Stage 4 | m050/docs/v0.5/governance/M050_MSID_Grammar_v0_5_MEDIANv0_5_0.md | Do not treat legacy MSID mappings as accepted decisions.
5 | Stage 2 — core game evidence | M050-SRC-HOME-001 | M050_Home_Mode_Colony_and_DWELL_Specification_v1_0_MEDIANv0_5_0.md | Home Mode, Colony, and DWELL specification | Source-bounded atomic extraction | 58 | Legacy dry run only; recalculate under Gate 5 | Dry run only; not extracted | 0 | Re-profile and calibrate after Gate 5 passes | m050/docs/v0.5/specifications/M050_Home_Mode_Colony_and_DWELL_Specification_v1_0_MEDIANv0_5_0.md | The 58-chunk plan belongs to the retired runner and is planning evidence only.
6 | Stage 2 — core game evidence | M050-SRC-EMBODIMENT-001 | M050_Embodiment_Register_and_EMBODY_Specification_v2_0_MEDIANv0_5_0.md | Embodiment and EMBODY specification | Source-bounded atomic extraction |  | Not planned under Gate 5 | Not started | 0 | Create identity card and dry-run chunk plan | m050/docs/v0.5/specifications/M050_Embodiment_Register_and_EMBODY_Specification_v2_0_MEDIANv0_5_0.md
7 | Stage 2 — core game evidence | M050-SRC-AWAY-001 | M050_Away_Mode_Field_Crossing_Encounter_and_Return_Specification_v1_0_MEDIANv0_5_0.md | Away Mode, Field, Crossing, Encounter, and Return | Source-bounded atomic extraction |  | Not planned under Gate 5 | Not started | 0 | Create identity card and dry-run chunk plan | m050/docs/v0.5/specifications/M050_Away_Mode_Field_Crossing_Encounter_and_Return_Specification_v1_0_MEDIANv0_5_0.md
8 | Stage 2 — core game evidence | M050-SRC-CROSSING-001 | M050_Crossing_Register_and_RISK_Specification_v0_1_MEDIANv0_5_0.md | Working Crossing and RISK specification | Migrate grounded evidence into Layer E | 11 | Completed legacy run | Legacy accepted; migration repairs required | 121 | Re-derive source status and review compound/table records | m050/docs/v0.5/specifications/M050_Crossing_Register_and_RISK_Specification_v0_1_MEDIANv0_5_0.md | No paid re-extraction required.
9 | Stage 2 — core game evidence | M050-SRC-POPULATION-001 | M050_Population_Growth_and_Colony_Tiers_Specification_v1_0_MEDIANv0_5_0.md | Population growth and colony tiers | Source-bounded atomic extraction |  | Not planned under Gate 5 | Not started | 0 | Create identity card and dry-run chunk plan | m050/docs/v0.5/specifications/M050_Population_Growth_and_Colony_Tiers_Specification_v1_0_MEDIANv0_5_0.md
10 | Stage 2 — core game evidence | M050-SRC-GUEST-001 | M050_Guest_Citizen_Specification_v2_0_MEDIANv0_5_0.md | Guest Citizen specification | Source-bounded atomic extraction |  | Not planned under Gate 5 | Not started | 0 | Create identity card and dry-run chunk plan | m050/docs/v0.5/specifications/M050_Guest_Citizen_Specification_v2_0_MEDIANv0_5_0.md
11 | Stage 2 — core game evidence | M050-SRC-PERSONAL-ITEMS-001 | M050_Personal_Items_Focus_and_Expedition_Equipment_Specification_v1_0_MEDIANv0_5_0.md | Personal items, Focus, and expedition equipment | Source-bounded atomic extraction |  | Not planned under Gate 5 | Not started | 0 | Create identity card and dry-run chunk plan | m050/docs/v0.5/specifications/M050_Personal_Items_Focus_and_Expedition_Equipment_Specification_v1_0_MEDIANv0_5_0.md
12 | Stage 2 — core game evidence | M050-SRC-DISCOVERY-TIME-PROGRESSION-001 | M050_Discovery_Time_Movement_and_Civic_Progression_Specification_v1_0_MEDIANv0_5_0.md | Discovery, time, movement, and civic progression | Source-bounded atomic extraction |  | Not planned under Gate 5 | Not started | 0 | Create identity card and dry-run chunk plan | m050/docs/v0.5/specifications/M050_Discovery_Time_Movement_and_Civic_Progression_Specification_v1_0_MEDIANv0_5_0.md
13 | Stage 2 — core game evidence | M050-SRC-CORE-TRAITS-001 | M050_Core_Species_Traits_Specification_v0_1_MEDIANv0_5_0.md | Working core species physical traits | Source-bounded atomic extraction |  | Not planned under Gate 5 | Not started | 0 | Create identity card and dry-run chunk plan | m050/docs/v0.5/specifications/M050_Core_Species_Traits_Specification_v0_1_MEDIANv0_5_0.md
14 | Stage 2 — bridge evidence | M050-SRC-047-CROSS-SYSTEM-CARRYFORWARD-001 | M050_v0_4_7_Cross_System_Attention_Persistence_and_World_State_Carryforward_v1_0_MEDIANv0_5_0.md | v0.4.7-to-v0.5 cross-system carryforward | Extract before grand reconciliation |  | Not planned under Gate 5 | Not started | 0 | Extract every substantive claim; retain status for reconciliation | m050/docs/v0.5/specifications/M050_v0_4_7_Cross_System_Attention_Persistence_and_World_State_Carryforward_v1_0_MEDIANv0_5_0.md | Dedicated descendants do not erase unique rules by silence.
15 | Stage 2 — subsidiary evidence | M050-SRC-ECOLOGY-001 | M050_Ecological_Influences_Specification_v1_0_MEDIANv0_5_0.md | Subsidiary ecological translation | Source-bounded atomic extraction |  | Not planned under Gate 5 | Not started | 0 | Extract, preserving subsidiary status for reconciliation | m050/docs/v0.5/specifications/M050_Ecological_Influences_Specification_v1_0_MEDIANv0_5_0.md
16 | Stage 2 — coverage-gap evidence | M050-SRC-GDD-COVERAGE-GAP-001 | M050_v0_4_6_GDD_Coverage_Gap_Development_v1_0_MEDIANv0_5_0.md | Late v0.4.6 GDD coverage-gap development | Extract before grand reconciliation |  | Not planned under Gate 5 | Not started | 0 | Map claims by actual subject; do not infer global ownership | m050/docs/v0.5/specifications/M050_v0_4_6_GDD_Coverage_Gap_Development_v1_0_MEDIANv0_5_0.md | Title and internal rhetoric confer no authority.
17 | Stage 2 — bridge/provenance evidence | M050-SRC-047-DEVELOPMENT-RULINGS-001 | M050_v0_4_7_Development_Rulings_Ledger_BSA_01_to_11A_Checkpoint_2026_07_30_MEDIANv0_5_0.md | v0.4.7-to-v0.5 adaptation and disposition ledger | Extract and partition before reconciliation |  | Not planned under Gate 5 | Not started | 0 | Separate substantive rules from lineage and process commentary | m050/docs/v0.5/provenance/M050_v0_4_7_Development_Rulings_Ledger_BSA_01_to_11A_Checkpoint_2026_07_30_MEDIANv0_5_0.md | Not a v0.4.6 baseline audit.
18 | Stage 2 — bridge/provenance evidence | M050-SRC-047-SURVIVORSHIP-REVIEW-001 | M050_v0_4_7_Development_Survivorship_Review_v0_1_MEDIANv0_5_0.md | v0.4.7 decision-development survivorship review | Extract and partition before reconciliation |  | Not planned under Gate 5 | Not started | 0 | Preserve findings and statuses; partition diagnostic prose | m050/docs/v0.5/provenance/M050_v0_4_7_Development_Survivorship_Review_v0_1_MEDIANv0_5_0.md | Not a v0.4.6 baseline audit.
19 | Stage 6 — baseline audit | M050-SRC-GDD-046-001 | M046_MEDIAN_Game_Design_Document_v0_4_6.md | Actual v0.4.6 revision baseline | Post-reconciliation grounded coverage audit |  | Planned only after Stage 5 | Deferred to Stage 6 | 0 | Process only after the reconciled v0.5 target exists | m050/docs/baseline/M046_MEDIAN_Game_Design_Document_v0_4_6.md | Historical baseline; not a current-source owner.
20 | Stage 7 — manifestation stream | M050-SRC-FOUR-MANIFESTATION-FRAMEWORK-001 | M050_Computer_TTRPG_Card_and_Mobile_Manifestation_Framework_v1_0_MEDIANv0_5_0.md | Cross-medium invariants and medium-specific rules | Deferred source-bounded extraction |  | Planned after core reconciliation | Deferred to Stage 7 | 0 | Extract into manifestation stream after core reconciliation | m050/docs/v0.5/specifications/M050_Computer_TTRPG_Card_and_Mobile_Manifestation_Framework_v1_0_MEDIANv0_5_0.md | Must not be flattened into core game semantics.
21 | Stage 7 — publication stream | M050-SRC-APPENDIX-001 | M050_Appendix_Architecture_and_Content_Plan_v1_0_MEDIANv0_5_0.md | Sourcebook and appendix publication architecture | Deterministic publication-control parse |  | Not applicable | Deterministic parse pending | 0 | Parse without model extraction during Stage 7 | m050/docs/v0.5/specifications/M050_Appendix_Architecture_and_Content_Plan_v1_0_MEDIANv0_5_0.md | Model extraction is prohibited.
22 | Stage 7 — optional manifestation | M050-SRC-BOARD-GAME-DRAFT-001 | M050_Board_Game_Manifestation_Initial_Draft_v0_1_MEDIANv0_5_0.md | Exploratory board-game manifestation | Deferred optional extraction |  | Only if selected for v0.5.0 | Deferred; selection unresolved | 0 | Human decision whether it belongs in v0.5.0 Sourcebook | m050/docs/v0.5/companions/M050_Board_Game_Manifestation_Initial_Draft_v0_1_MEDIANv0_5_0.md | Does not block core extraction or reconciliation.
23 | Reference only | M050-SRC-MARKET-001 | M050_Market_Position_Comparative_Landscape_and_Resemblance_Risk_Research_v1_1_MEDIANv0_5_0.md | Positioning and comparative analysis | Retain companion; no compile extraction |  | Not applicable | No extraction — reference only | 0 | Retain outside the atomic compile | m050/docs/v0.5/companions/M050_Market_Position_Comparative_Landscape_and_Resemblance_Risk_Research_v1_1_MEDIANv0_5_0.md
24 | Reference only | M050-SRC-SOURCEBOOK-AUGMENTS-001 | M050_Sourcebook_Visual_Narrative_and_Infographic_Augments_Plan_v0_1_MEDIANv0_5_0.md | Production and illustration plan | Retain companion; no compile extraction |  | Not applicable | No extraction — reference only | 0 | Retain outside the atomic compile | m050/docs/v0.5/companions/M050_Sourcebook_Visual_Narrative_and_Infographic_Augments_Plan_v0_1_MEDIANv0_5_0.md