## Progress & Stages
MEDIAN v0.5.0 Compile Progress & Stage Guide | MEDIAN v0.5.0 Compile Progress & Stage Guide | MEDIAN v0.5.0 Compile Progress & Stage Guide | MEDIAN v0.5.0 Compile Progress & Stage Guide | MEDIAN v0.5.0 Compile Progress & Stage Guide | MEDIAN v0.5.0 Compile Progress & Stage Guide | MEDIAN v0.5.0 Compile Progress & Stage Guide
Current state after Gates 1–3 and the ongoing Gate 4 cleanup. Costs are intentionally excluded and remain under m050/docs/operations/costs. | Current state after Gates 1–3 and the ongoing Gate 4 cleanup. Costs are intentionally excluded and remain under m050/docs/operations/costs. | Current state after Gates 1–3 and the ongoing Gate 4 cleanup. Costs are intentionally excluded and remain under m050/docs/operations/costs. | Current state after Gates 1–3 and the ongoing Gate 4 cleanup. Costs are intentionally excluded and remain under m050/docs/operations/costs. | Current state after Gates 1–3 and the ongoing Gate 4 cleanup. Costs are intentionally excluded and remain under m050/docs/operations/costs. | Current state after Gates 1–3 and the ongoing Gate 4 cleanup. Costs are intentionally excluded and remain under m050/docs/operations/costs. | Current state after Gates 1–3 and the ongoing Gate 4 cleanup. Costs are intentionally excluded and remain under m050/docs/operations/costs.
Current metric | Value |  | Gate summary | Value
Current control gate | Gate 4 — source identity and drift retirement |  | Completed gates | 3
Completed legacy extractions | 4 |  | Gates in progress | 1
External model calls | Frozen until Gate 5 implementation and dry-run verification |  | Next controlling decision | Finish Gate 4, then specify and verify Gate 5 implementation
Control gates | Control gates | Control gates | Control gates | Control gates | Control gates | Control gates
Gate | Purpose | Plain-language meaning | Status | Evidence | Pass condition | Next action
Gate 1 | Process diagnosis | Identify drift, scope growth, and contamination risks. | Complete | Gate 1 diagnosis | State of affairs documented | Retain as process evidence
Gate 2 | Target process | Define actual outcome, streams, source roles, stages, and error correction. | Complete | Gate 2 process and source disposition | Target architecture accepted | Use as the controlling design
Gate 3 | Legacy extraction reuse | Determine whether four completed extractions are grounded and reusable. | Complete | Gate 3 reuse audit | Reuse with mandatory migration repairs | Migrate evidence in Gate 5; no wholesale rerun
Gate 4 | Identity and repository cleanup | Correct misleading names and retire drift-era controls and run artifacts. | In progress | Renames and archival substantially complete | Final validation and completion receipt | Finish repository-wide checks and tracker refresh
Gate 5 | Implementation verification | Build the simpler source-bounded extraction system and prove it offline. | Not started | No active runner yet | Verified dry run and controlled calibration approval | Begin only after Gate 4 passes
Target processing stages | Target processing stages | Target processing stages | Target processing stages | Target processing stages | Target processing stages | Target processing stages
Stage | Name | What it means | Method | Current status | Pass condition | Next action
Stage 0 | Source freeze and identity | Verify the exact file, hash, content-derived identity, role, streams, and exclusions. | No model | Pending Gate 5 implementation | Every work order passes the identity gate | Implement manifest validation
Stage 1 | Structural preparation | Create stable blocks and bounded chunks without crossing tables or status boundaries. | No model | Pending Gate 5 implementation | Complete block ledger and dry-run chunk plan | Implement block and dual-bound chunk controls
Stage 2 | Source-bounded extraction | Extract only one source's owned blocks; do not compare documents or assign final MSIDs. | Model + local controls | Four legacy runs await migration; remaining sources not started | Every block receives one disposition | Migrate reusable evidence, then calibrate fresh sources
Stage 3 | Validation and acceptance | Verify schema, hashes, quotations, locations, completeness, and compound-atom flags. | Deterministic + semantic review | Legacy evidence audited; new system not implemented | Accepted source evidence with receipts | Build validator and acceptance reports
Stage 4 | MSID vocabulary and mapping | Build the vocabulary from accepted MSID Grammar evidence, then map atoms separately. | Mapping layer | Not started | Every atom mapped, ambiguous, unmapped, invalid, or human-required | Start only after accepted evidence exists
Stage 5 | Grand reconciliation | Compare validated sources, apply authority and human rulings, and resolve or expose conflicts. | Cross-source review | Not started | Every substantive atom has an explicit disposition | Do not begin during extraction
Stage 6 | v0.4.6 baseline audit | Compare the reconciled v0.5 target against the actual v0.4.6 GDD baseline. | Coverage audit | Not started | Every baseline subject has a survivorship or gap disposition | Run after Stage 5
Stage 7 | Manifestation and publication | Reconcile medium-specific rules and compile publication controls separately from core rules. | Separate streams | Not started | Manifestation and publication records are reconciled | Run after core reconciliation
Stage 8 | Compilation and bidirectional audit | Produce readable v0.5 documents with traceability from source to output and back. | Compiler + QA | Not started | No unsupported compiled claim and no silent loss | Final stage